# Project Schedule

|  |  |  |
| --- | --- | --- |
| **Activity** | **Predecessor** | **Duration(Days)** |
| Support | - | 5 |
| Confidence | Support | 3 |
| Lift | Support | 2 |
| Leverage | Support | 2 |
| Report | Support,Confidence,lift,leverage | 3 |
| Demo | Report | 2 |
| Presentation | Report | 3 |

# Gantt Chart

Report Day

# Earned value analysis

|  |  |  |  |
| --- | --- | --- | --- |
| Tasks | Earned value | Planned value | Schedule variance |
| Support | 100 | 100 | 0 |
| Confidence | 80 | 100 | -20 |
| Lift | 90 | 100 | -10 |
| Leverage | 90 | 100 | -10 |
| Report | 70 | 0 | 70 |
| Demo | 0 | 0 | 0 |
| Presentation | 0 | 0 | 0   |  | | --- | | Total: 30 | |

Therefore the project is ahead of schedule by 30 %